## 📊 Dashboard
☸ SARVEDA — Requirements Traceability Matrix
eCommerce Platform Migration · Version 1.0 · Generated: 25 May 2026 · Confidential
Total Requirements |  | Must Have |  | Complete |  | In Progress |  | Tests Passed
130 |  | 98 |  | 50 |  | 15 |  | 43
MODULE BREAKDOWN
Module | Total | Must Have | Should Have | Nice to Have | Not Started | In Progress | Complete | Tests Passed | % Done
Authentication | 7 | 6 | 1 | 0 | 2 | 1 | 4 | 4 | 57%
Products | 18 | 11 | 4 | 3 | 7 | 2 | 9 | 9 | 50%
Cart & Checkout | 11 | 8 | 3 | 0 | 4 | 2 | 5 | 5 | 45%
Payments | 11 | 9 | 1 | 1 | 5 | 2 | 4 | 4 | 36%
Orders | 11 | 9 | 2 | 0 | 3 | 3 | 5 | 5 | 45%
Shipping | 8 | 8 | 0 | 0 | 0 | 3 | 5 | 1 | 62%
Notifications | 12 | 10 | 2 | 0 | 12 | 0 | 0 | 0 | 0%
Zoho | 8 | 5 | 3 | 0 | 7 | 0 | 1 | 1 | 12%
Admin Panel | 11 | 9 | 2 | 0 | 6 | 2 | 3 | 3 | 27%
UI/UX | 9 | 3 | 3 | 3 | 4 | 0 | 5 | 2 | 55%
Infrastructure | 10 | 10 | 0 | 0 | 2 | 0 | 8 | 8 | 80%
Courses | 7 | 5 | 1 | 1 | 7 | 0 | 0 | 0 | 0%
Marketing | 7 | 5 | 1 | 1 | 6 | 0 | 1 | 1 | 14%
LEGEND
Must Have |  |  | Should Have |  |  | Nice to Have
Not Started |  |  | In Progress |  |  | Complete
Pass ✅ |  |  | Fail ❌ |  |  | Not Tested

## 📋 Full RTM
☸ SARVEDA — Full Requirements Traceability Matrix
REQ ID | Module | Requirement Description | Source | Priority | Design Status | Dev Status | Test Status | Test Evidence | Sprint | Notes / Comments | Date Added | Date Completed | Sign-off
▶ AUTHENTICATION
REQ-AUTH-001 | Authentication | Customer can register with email and password | Arjun | Must Have | Complete | Complete | Pass | GoogleSignInButton.tsx / auth routes | Sprint 1
REQ-AUTH-002 | Authentication | Customer can login with Google OAuth | Arjun | Must Have | Complete | Complete | Pass | Google OAuth flow tested | Sprint 1 | New Google credentials set up for sarveda-demo.xyz
REQ-AUTH-003 | Authentication | Customer can reset password via email | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 1
REQ-AUTH-004 | Authentication | JWT token issued on login, expires in 7 days | Technical | Must Have | Complete | Complete | Pass | Auth middleware verified | Sprint 1
REQ-AUTH-005 | Authentication | Admin panel protected — only admin roles can access | Arjun | Must Have | Complete | Complete | Pass | AdminAuthBoundary.tsx | Sprint 1
REQ-AUTH-006 | Authentication | Multiple admin roles: Super Admin, Order Manager, Inventory, Marketing, Finance | Arjun | Must Have | In Progress | Not Started | Not Tested |  | Sprint 2 | To be defined post requirements meeting
REQ-AUTH-007 | Authentication | Session auto-logout after inactivity | Technical | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
▶ PRODUCTS
REQ-PROD-001 | Products | 169 products migrated from WooCommerce | Arjun | Must Have | Complete | Complete | Pass | CSV import done | Sprint 1
REQ-PROD-002 | Products | Products have multiple images | Arjun | Must Have | Complete | Complete | Pass | Product page verified | Sprint 1
REQ-PROD-003 | Products | Products have variants (size, weight, note/tone) | Arjun | Must Have | Complete | Complete | Pass | VariantShippingRate seeded | Sprint 1
REQ-PROD-004 | Products | Audio samples on singing bowl products | Arjun | Must Have | Complete | Complete | Pass | hasAudio flag in DB | Sprint 1 | Unique differentiator — promote loudly
REQ-PROD-005 | Products | Product categories with hierarchical structure | Arjun | Must Have | Complete | Complete | Pass | CategoryTree API | Sprint 1
REQ-PROD-006 | Products | Stock level shown on product page | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-PROD-007 | Products | Low stock badge when stock ≤ 5 units | Arjun | Should Have | Complete | Complete | Pass | productListBadges() | Sprint 1
REQ-PROD-008 | Products | Out of stock badge — disable add to cart | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-PROD-009 | Products | Related products section on product page | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PROD-010 | Products | Customer reviews and star ratings on product page | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PROD-011 | Products | Pincode serviceability check before add to cart | Arjun | Must Have | Complete | Complete | Pass | check-pincode API ✅ | Sprint 2 | Tested: pincode 517501 returns serviceable:true, estimatedDays:5
REQ-PROD-012 | Products | Estimated delivery date shown on product page | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-PROD-013 | Products | Product search with filters (category, price, weight) | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-PROD-014 | Products | GST/HSN codes on products for invoicing | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PROD-015 | Products | Artisan/source story on product page | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-PROD-016 | Products | Product video embed support | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-PROD-017 | Products | Wishlist / Save for later | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-PROD-018 | Products | Bulk product import/export via CSV | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
▶ CART & CHECKOUT
REQ-CART-001 | Cart & Checkout | Add to cart with variant selection | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-CART-002 | Cart & Checkout | Cart persists across sessions (logged in user) | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-CART-003 | Cart & Checkout | Stock reserved on add to cart — released if not paid in 15 min | Technical | Must Have | Complete | Complete | Pass | BullMQ payment timeout job | Sprint 1 | Day 1 hardening complete
REQ-CART-004 | Cart & Checkout | Cart drawer slides in from right (mobile + desktop) | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-CART-005 | Cart & Checkout | Free shipping threshold indicator in cart | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3 | e.g. Add ₹299 more for free shipping
REQ-CART-006 | Cart & Checkout | Coupon code application at checkout | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 2
REQ-CART-007 | Cart & Checkout | Guest checkout (without account) | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-CART-008 | Cart & Checkout | Address form with pincode auto-fill (city/state) | Arjun | Must Have | Complete | Complete | Pass | AddressFields.tsx | Sprint 1
REQ-CART-009 | Cart & Checkout | Shipping cost calculated from VariantShippingRate table | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2 | Was hardcoded to 0 — fixed in checkout.service.ts
REQ-CART-010 | Cart & Checkout | Order summary with GST breakdown at checkout | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-CART-011 | Cart & Checkout | Abandoned cart recovery — WhatsApp/Email reminder | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
▶ PAYMENTS
REQ-PAY-001 | Payments | Razorpay integration — India payments (UPI, cards, netbanking) | Arjun | Must Have | Complete | Complete | Pass | Razorpay webhook live | Sprint 1 | New Razorpay keys configured for sarveda.com account
REQ-PAY-002 | Payments | Stripe integration — international payments | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2 | Backend done — frontend needs testing
REQ-PAY-003 | Payments | PayPal integration — international payments | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2 | Backend done — frontend needs testing
REQ-PAY-004 | Payments | COD (Cash on Delivery) — India only | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 2
REQ-PAY-005 | Payments | Payment webhook verification (signature check) | Technical | Must Have | Complete | Complete | Pass | HMAC verification in webhook handler | Sprint 1 | Idempotency keys implemented
REQ-PAY-006 | Payments | Payment failure page with retry option | Arjun | Must Have | Complete | Complete | Pass | payment-failed page | Sprint 1
REQ-PAY-007 | Payments | Idempotency keys — prevent double charging | Technical | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-PAY-008 | Payments | Refund processing via payment gateway | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PAY-009 | Payments | Multi-currency support — INR, USD, GBP | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PAY-010 | Payments | Currency switcher on frontend | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PAY-011 | Payments | EMI options via Razorpay | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
▶ ORDERS
REQ-ORD-001 | Orders | Order confirmation page after payment | Arjun | Must Have | Complete | Complete | Pass | order/confirmed page | Sprint 1
REQ-ORD-002 | Orders | Order status lifecycle: Pending → Paid → Processing → Shipped → Delivered | Arjun | Must Have | Complete | Complete | Pass | OrderStatus enum | Sprint 1
REQ-ORD-003 | Orders | Customer can view all past orders in My Account | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2
REQ-ORD-004 | Orders | Customer can view single order detail | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2
REQ-ORD-005 | Orders | Customer can download GST invoice from order page | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ORD-006 | Orders | Admin can view and filter all orders | Arjun | Must Have | Complete | Complete | Pass | Admin orders page | Sprint 1
REQ-ORD-007 | Orders | Admin can update order status manually | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-ORD-008 | Orders | Admin can cancel order and trigger refund | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ORD-009 | Orders | Order auto-cancels if payment not received in 15 min | Technical | Must Have | Complete | Complete | Pass | BullMQ timeout job | Sprint 1
REQ-ORD-010 | Orders | Order tracking page with AWB (public URL) | Arjun | Should Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-ORD-011 | Orders | RTO (Return to Origin) status handling | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
▶ SHIPPING
REQ-SHIP-001 | Shipping | Delhivery API integration — domestic India | Arjun | Must Have | Complete | Complete | Not Tested | shipping/delhivery.ts | Sprint 2 | Built today — needs end-to-end test with real API key
REQ-SHIP-002 | Shipping | Shiprocket integration — international orders | Arjun | Must Have | Complete | Complete | Not Tested | shipping/shiprocket.ts | Sprint 2
REQ-SHIP-003 | Shipping | Auto courier selection router (weight + zone + COD logic) | Technical | Must Have | Complete | Complete | Not Tested | shipping/router.ts | Sprint 2
REQ-SHIP-004 | Shipping | AWB auto-generated when order moves to PROCESSING | Arjun | Must Have | Complete | In Progress | Not Tested | shipping/orderLifecycle.ts | Sprint 2
REQ-SHIP-005 | Shipping | Pincode serviceability check — India | Arjun | Must Have | Complete | Complete | Pass | check-pincode API tested ✅ | Sprint 2
REQ-SHIP-006 | Shipping | Shipping cost from VariantShippingRate — India and International | Arjun | Must Have | Complete | In Progress | Not Tested | checkout.service.ts | Sprint 2 | Previously hardcoded to 0
REQ-SHIP-007 | Shipping | International shipping rates by country (US/GB/OTHER) | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2
REQ-SHIP-008 | Shipping | No COD for international orders — enforced | Technical | Must Have | Complete | Complete | Not Tested |  | Sprint 2
▶ NOTIFICATIONS
REQ-NOT-001 | Notifications | Email — Order confirmed | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Day 2 target — SendGrid
REQ-NOT-002 | Notifications | Email — Payment failed | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-003 | Notifications | Email — Order shipped with tracking link | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-004 | Notifications | Email — Order delivered | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-005 | Notifications | Email — GST invoice attached | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-006 | Notifications | WhatsApp — Order confirmed (WATI) | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | WATI integration pending
REQ-NOT-007 | Notifications | WhatsApp — Shipment dispatched with AWB | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-008 | Notifications | WhatsApp — Out for delivery | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-009 | Notifications | WhatsApp — Order delivered + review request | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-010 | Notifications | GST PDF invoice auto-generated on PAID status | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | PDFKit planned
REQ-NOT-011 | Notifications | BullMQ email queue — retry on failure | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-012 | Notifications | BullMQ WhatsApp queue — retry on failure | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
▶ ZOHO
REQ-ZOHO-001 | Zoho | Order paid on Sarveda → auto create Sales Order in Zoho Inventory | Arjun | Must Have | Complete | Complete | Pass | Level 2 integration live | Sprint 1 | Working currently
REQ-ZOHO-002 | Zoho | Stock updated in Zoho → reflect on Sarveda website | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Level 3 upgrade
REQ-ZOHO-003 | Zoho | Customer data sync to Zoho CRM | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ZOHO-004 | Zoho | Shipment AWB synced back from Zoho to Sarveda | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ZOHO-005 | Zoho | Refund recorded in Zoho Books when processed | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-ZOHO-006 | Zoho | Nightly full stock sync (safety net) | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Scheduled BullMQ job at 2AM
REQ-ZOHO-007 | Zoho | Sync failure alert to admin if Zoho order creation fails | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ZOHO-008 | Zoho | RTO return → stock added back in Zoho Inventory | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 4
▶ ADMIN PANEL
REQ-ADM-001 | Admin Panel | Dashboard: today's orders, revenue, pending, low stock | Arjun | Must Have | Complete | Complete | Pass | Admin dashboard | Sprint 1
REQ-ADM-002 | Admin Panel | Product CRUD — add, edit, delete products | Arjun | Must Have | Complete | Complete | Pass | Admin products | Sprint 1
REQ-ADM-003 | Admin Panel | Order management — filter by status, date, customer | Arjun | Must Have | Complete | Complete | Pass | Admin orders page | Sprint 1
REQ-ADM-004 | Admin Panel | Inventory management — update stock levels | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-ADM-005 | Admin Panel | Customer management — view all customers | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-006 | Admin Panel | Coupon/discount management | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-007 | Admin Panel | Revenue reports — daily, weekly, monthly | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-008 | Admin Panel | GST report for CA/accounting | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-009 | Admin Panel | Low stock alert system | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-010 | Admin Panel | Admin mobile responsive — works on phone | Arjun | Should Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-ADM-011 | Admin Panel | Role-based access control (RBAC) | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | To define roles post requirements meeting
▶ UI/UX
REQ-UX-001 | UI/UX | Mobile-first design — Android app feel | Arjun | Must Have | Complete | Complete | Pass | BottomNav, warm cream theme | Sprint 2 | Premium redesign applied
REQ-UX-002 | UI/UX | Bottom navigation bar on mobile | Arjun | Must Have | Complete | Complete | Pass | BottomNav.tsx | Sprint 2
REQ-UX-003 | UI/UX | Announcement bar (free shipping, offers) | Arjun | Should Have | Complete | Complete | Not Tested | Header.tsx / SiteHeader.tsx | Sprint 2
REQ-UX-004 | UI/UX | Premium homepage — hero, categories, testimonials | Arjun | Must Have | Complete | Complete | Not Tested | app/page.tsx redesigned | Sprint 2
REQ-UX-005 | UI/UX | Page transitions — smooth navigation | Arjun | Should Have | Complete | Complete | Not Tested | PageTransition.tsx | Sprint 2
REQ-UX-006 | UI/UX | PWA support — Add to Home Screen | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-UX-007 | UI/UX | Framer Motion scroll animations | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-UX-008 | UI/UX | Custom gold cursor effect on desktop | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-UX-009 | UI/UX | Skeleton loaders on all data-fetching pages | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
▶ INFRASTRUCTURE
REQ-INF-001 | Infrastructure | Frontend deployed on Vercel | Technical | Must Have | Complete | Complete | Pass | sarveda-frontend.vercel.app | Sprint 1
REQ-INF-002 | Infrastructure | Backend deployed on AWS EC2 Mumbai | Technical | Must Have | Complete | Complete | Pass | 13.206.192.106:5000 | Sprint 1
REQ-INF-003 | Infrastructure | PostgreSQL on AWS RDS | Technical | Must Have | Complete | Complete | Pass | sarveda-db RDS | Sprint 1
REQ-INF-004 | Infrastructure | Redis on EC2 for BullMQ | Technical | Must Have | Complete | Complete | Pass | localhost:6379 | Sprint 1
REQ-INF-005 | Infrastructure | sarveda-demo.xyz domain purchased and configured | Technical | Must Have | Complete | Complete | Pass | Bought on Vercel $1.99 | Sprint 2
REQ-INF-006 | Infrastructure | SSL/HTTPS on EC2 backend (nginx + certbot) | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 5 | Needed for Google OAuth + webhooks
REQ-INF-007 | Infrastructure | api.sarveda-demo.xyz subdomain for backend | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 5
REQ-INF-008 | Infrastructure | PM2 process manager for backend uptime | Technical | Must Have | Complete | Complete | Pass | sarveda-backend PM2 | Sprint 1
REQ-INF-009 | Infrastructure | Razorpay webhook configured and verified | Technical | Must Have | Complete | Complete | Pass | Webhook set up | Sprint 2
REQ-INF-010 | Infrastructure | Google OAuth credentials for sarveda-demo.xyz | Technical | Must Have | Complete | Complete | Pass | New Sarveda project in GCP | Sprint 2
▶ COURSES
REQ-CRS-001 | Courses | Course listing page | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-CRS-002 | Courses | Course purchase flow with Stripe/PayPal | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4 | International buyers primary
REQ-CRS-003 | Courses | Student portal — access purchased courses | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-CRS-004 | Courses | Live session Zoom link delivery after purchase | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-CRS-005 | Courses | Pre-recorded video course playback | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-CRS-006 | Courses | Course completion certificate | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 5
REQ-CRS-007 | Courses | Himalayan Retreat booking page with $900 pricing | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4 | Highest ticket — priority
▶ MARKETING
REQ-MKT-001 | Marketing | Google Analytics 4 integration | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Critical — start tracking from day 1
REQ-MKT-002 | Marketing | Meta/Facebook Pixel integration | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-MKT-003 | Marketing | Newsletter signup with email collection | Arjun | Must Have | Complete | Complete | Pass | NewsletterForm.tsx | Sprint 2
REQ-MKT-004 | Marketing | Coupon code system — % and flat discount | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-MKT-005 | Marketing | SEO — meta tags, OG tags, sitemap | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-MKT-006 | Marketing | Referral / affiliate program | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 5
REQ-MKT-007 | Marketing | WELCOME10 — 10% first order coupon | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Already in announcement bar copy

## 🔐 Authentication
🔐 Authentication — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-AUTH-001 | Customer can register with email and password | Arjun | Must Have | Complete | Complete | Pass | GoogleSignInButton.tsx / auth routes | Sprint 1
REQ-AUTH-002 | Customer can login with Google OAuth | Arjun | Must Have | Complete | Complete | Pass | Google OAuth flow tested | Sprint 1 | New Google credentials set up for sarveda-demo.xyz
REQ-AUTH-003 | Customer can reset password via email | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 1
REQ-AUTH-004 | JWT token issued on login, expires in 7 days | Technical | Must Have | Complete | Complete | Pass | Auth middleware verified | Sprint 1
REQ-AUTH-005 | Admin panel protected — only admin roles can access | Arjun | Must Have | Complete | Complete | Pass | AdminAuthBoundary.tsx | Sprint 1
REQ-AUTH-006 | Multiple admin roles: Super Admin, Order Manager, Inventory, Marketing, Finance | Arjun | Must Have | In Progress | Not Started | Not Tested |  | Sprint 2 | To be defined post requirements meeting
REQ-AUTH-007 | Session auto-logout after inactivity | Technical | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3

## 📦 Products
📦 Products — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-PROD-001 | 169 products migrated from WooCommerce | Arjun | Must Have | Complete | Complete | Pass | CSV import done | Sprint 1
REQ-PROD-002 | Products have multiple images | Arjun | Must Have | Complete | Complete | Pass | Product page verified | Sprint 1
REQ-PROD-003 | Products have variants (size, weight, note/tone) | Arjun | Must Have | Complete | Complete | Pass | VariantShippingRate seeded | Sprint 1
REQ-PROD-004 | Audio samples on singing bowl products | Arjun | Must Have | Complete | Complete | Pass | hasAudio flag in DB | Sprint 1 | Unique differentiator — promote loudly
REQ-PROD-005 | Product categories with hierarchical structure | Arjun | Must Have | Complete | Complete | Pass | CategoryTree API | Sprint 1
REQ-PROD-006 | Stock level shown on product page | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-PROD-007 | Low stock badge when stock ≤ 5 units | Arjun | Should Have | Complete | Complete | Pass | productListBadges() | Sprint 1
REQ-PROD-008 | Out of stock badge — disable add to cart | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-PROD-009 | Related products section on product page | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PROD-010 | Customer reviews and star ratings on product page | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PROD-011 | Pincode serviceability check before add to cart | Arjun | Must Have | Complete | Complete | Pass | check-pincode API ✅ | Sprint 2 | Tested: pincode 517501 returns serviceable:true, estimatedDays:5
REQ-PROD-012 | Estimated delivery date shown on product page | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-PROD-013 | Product search with filters (category, price, weight) | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-PROD-014 | GST/HSN codes on products for invoicing | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PROD-015 | Artisan/source story on product page | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-PROD-016 | Product video embed support | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-PROD-017 | Wishlist / Save for later | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-PROD-018 | Bulk product import/export via CSV | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3

## 🛒 Cart and Checkout
🛒 Cart & Checkout — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-CART-001 | Add to cart with variant selection | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-CART-002 | Cart persists across sessions (logged in user) | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-CART-003 | Stock reserved on add to cart — released if not paid in 15 min | Technical | Must Have | Complete | Complete | Pass | BullMQ payment timeout job | Sprint 1 | Day 1 hardening complete
REQ-CART-004 | Cart drawer slides in from right (mobile + desktop) | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-CART-005 | Free shipping threshold indicator in cart | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3 | e.g. Add ₹299 more for free shipping
REQ-CART-006 | Coupon code application at checkout | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 2
REQ-CART-007 | Guest checkout (without account) | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-CART-008 | Address form with pincode auto-fill (city/state) | Arjun | Must Have | Complete | Complete | Pass | AddressFields.tsx | Sprint 1
REQ-CART-009 | Shipping cost calculated from VariantShippingRate table | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2 | Was hardcoded to 0 — fixed in checkout.service.ts
REQ-CART-010 | Order summary with GST breakdown at checkout | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-CART-011 | Abandoned cart recovery — WhatsApp/Email reminder | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3

## 💳 Payments
💳 Payments — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-PAY-001 | Razorpay integration — India payments (UPI, cards, netbanking) | Arjun | Must Have | Complete | Complete | Pass | Razorpay webhook live | Sprint 1 | New Razorpay keys configured for sarveda.com account
REQ-PAY-002 | Stripe integration — international payments | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2 | Backend done — frontend needs testing
REQ-PAY-003 | PayPal integration — international payments | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2 | Backend done — frontend needs testing
REQ-PAY-004 | COD (Cash on Delivery) — India only | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 2
REQ-PAY-005 | Payment webhook verification (signature check) | Technical | Must Have | Complete | Complete | Pass | HMAC verification in webhook handler | Sprint 1 | Idempotency keys implemented
REQ-PAY-006 | Payment failure page with retry option | Arjun | Must Have | Complete | Complete | Pass | payment-failed page | Sprint 1
REQ-PAY-007 | Idempotency keys — prevent double charging | Technical | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-PAY-008 | Refund processing via payment gateway | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PAY-009 | Multi-currency support — INR, USD, GBP | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PAY-010 | Currency switcher on frontend | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-PAY-011 | EMI options via Razorpay | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4

## 📋 Orders
📋 Orders — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-ORD-001 | Order confirmation page after payment | Arjun | Must Have | Complete | Complete | Pass | order/confirmed page | Sprint 1
REQ-ORD-002 | Order status lifecycle: Pending → Paid → Processing → Shipped → Delivered | Arjun | Must Have | Complete | Complete | Pass | OrderStatus enum | Sprint 1
REQ-ORD-003 | Customer can view all past orders in My Account | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2
REQ-ORD-004 | Customer can view single order detail | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2
REQ-ORD-005 | Customer can download GST invoice from order page | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ORD-006 | Admin can view and filter all orders | Arjun | Must Have | Complete | Complete | Pass | Admin orders page | Sprint 1
REQ-ORD-007 | Admin can update order status manually | Arjun | Must Have | Complete | Complete | Pass |  | Sprint 1
REQ-ORD-008 | Admin can cancel order and trigger refund | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ORD-009 | Order auto-cancels if payment not received in 15 min | Technical | Must Have | Complete | Complete | Pass | BullMQ timeout job | Sprint 1
REQ-ORD-010 | Order tracking page with AWB (public URL) | Arjun | Should Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-ORD-011 | RTO (Return to Origin) status handling | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3

## 🚚 Shipping
🚚 Shipping — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-SHIP-001 | Delhivery API integration — domestic India | Arjun | Must Have | Complete | Complete | Not Tested | shipping/delhivery.ts | Sprint 2 | Built today — needs end-to-end test with real API key
REQ-SHIP-002 | Shiprocket integration — international orders | Arjun | Must Have | Complete | Complete | Not Tested | shipping/shiprocket.ts | Sprint 2
REQ-SHIP-003 | Auto courier selection router (weight + zone + COD logic) | Technical | Must Have | Complete | Complete | Not Tested | shipping/router.ts | Sprint 2
REQ-SHIP-004 | AWB auto-generated when order moves to PROCESSING | Arjun | Must Have | Complete | In Progress | Not Tested | shipping/orderLifecycle.ts | Sprint 2
REQ-SHIP-005 | Pincode serviceability check — India | Arjun | Must Have | Complete | Complete | Pass | check-pincode API tested ✅ | Sprint 2
REQ-SHIP-006 | Shipping cost from VariantShippingRate — India and International | Arjun | Must Have | Complete | In Progress | Not Tested | checkout.service.ts | Sprint 2 | Previously hardcoded to 0
REQ-SHIP-007 | International shipping rates by country (US/GB/OTHER) | Arjun | Must Have | Complete | In Progress | Not Tested |  | Sprint 2
REQ-SHIP-008 | No COD for international orders — enforced | Technical | Must Have | Complete | Complete | Not Tested |  | Sprint 2

## 🔔 Notifications
🔔 Notifications — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-NOT-001 | Email — Order confirmed | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Day 2 target — SendGrid
REQ-NOT-002 | Email — Payment failed | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-003 | Email — Order shipped with tracking link | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-004 | Email — Order delivered | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-005 | Email — GST invoice attached | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-006 | WhatsApp — Order confirmed (WATI) | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | WATI integration pending
REQ-NOT-007 | WhatsApp — Shipment dispatched with AWB | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-008 | WhatsApp — Out for delivery | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-009 | WhatsApp — Order delivered + review request | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-010 | GST PDF invoice auto-generated on PAID status | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | PDFKit planned
REQ-NOT-011 | BullMQ email queue — retry on failure | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-NOT-012 | BullMQ WhatsApp queue — retry on failure | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3

## ⚙️ Zoho
⚙️ Zoho — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-ZOHO-001 | Order paid on Sarveda → auto create Sales Order in Zoho Inventory | Arjun | Must Have | Complete | Complete | Pass | Level 2 integration live | Sprint 1 | Working currently
REQ-ZOHO-002 | Stock updated in Zoho → reflect on Sarveda website | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Level 3 upgrade
REQ-ZOHO-003 | Customer data sync to Zoho CRM | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ZOHO-004 | Shipment AWB synced back from Zoho to Sarveda | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ZOHO-005 | Refund recorded in Zoho Books when processed | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-ZOHO-006 | Nightly full stock sync (safety net) | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Scheduled BullMQ job at 2AM
REQ-ZOHO-007 | Sync failure alert to admin if Zoho order creation fails | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ZOHO-008 | RTO return → stock added back in Zoho Inventory | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 4

## 🛠️ Admin Panel
🛠️ Admin Panel — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-ADM-001 | Dashboard: today's orders, revenue, pending, low stock | Arjun | Must Have | Complete | Complete | Pass | Admin dashboard | Sprint 1
REQ-ADM-002 | Product CRUD — add, edit, delete products | Arjun | Must Have | Complete | Complete | Pass | Admin products | Sprint 1
REQ-ADM-003 | Order management — filter by status, date, customer | Arjun | Must Have | Complete | Complete | Pass | Admin orders page | Sprint 1
REQ-ADM-004 | Inventory management — update stock levels | Arjun | Must Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-ADM-005 | Customer management — view all customers | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-006 | Coupon/discount management | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-007 | Revenue reports — daily, weekly, monthly | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-008 | GST report for CA/accounting | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-009 | Low stock alert system | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-ADM-010 | Admin mobile responsive — works on phone | Arjun | Should Have | In Progress | In Progress | Not Tested |  | Sprint 2
REQ-ADM-011 | Role-based access control (RBAC) | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | To define roles post requirements meeting

## 🎨 UI-UX
🎨 UI/UX — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-UX-001 | Mobile-first design — Android app feel | Arjun | Must Have | Complete | Complete | Pass | BottomNav, warm cream theme | Sprint 2 | Premium redesign applied
REQ-UX-002 | Bottom navigation bar on mobile | Arjun | Must Have | Complete | Complete | Pass | BottomNav.tsx | Sprint 2
REQ-UX-003 | Announcement bar (free shipping, offers) | Arjun | Should Have | Complete | Complete | Not Tested | Header.tsx / SiteHeader.tsx | Sprint 2
REQ-UX-004 | Premium homepage — hero, categories, testimonials | Arjun | Must Have | Complete | Complete | Not Tested | app/page.tsx redesigned | Sprint 2
REQ-UX-005 | Page transitions — smooth navigation | Arjun | Should Have | Complete | Complete | Not Tested | PageTransition.tsx | Sprint 2
REQ-UX-006 | PWA support — Add to Home Screen | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-UX-007 | Framer Motion scroll animations | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-UX-008 | Custom gold cursor effect on desktop | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-UX-009 | Skeleton loaders on all data-fetching pages | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3

## ☁️ Infrastructure
☁️ Infrastructure — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-INF-001 | Frontend deployed on Vercel | Technical | Must Have | Complete | Complete | Pass | sarveda-frontend.vercel.app | Sprint 1
REQ-INF-002 | Backend deployed on AWS EC2 Mumbai | Technical | Must Have | Complete | Complete | Pass | 13.206.192.106:5000 | Sprint 1
REQ-INF-003 | PostgreSQL on AWS RDS | Technical | Must Have | Complete | Complete | Pass | sarveda-db RDS | Sprint 1
REQ-INF-004 | Redis on EC2 for BullMQ | Technical | Must Have | Complete | Complete | Pass | localhost:6379 | Sprint 1
REQ-INF-005 | sarveda-demo.xyz domain purchased and configured | Technical | Must Have | Complete | Complete | Pass | Bought on Vercel $1.99 | Sprint 2
REQ-INF-006 | SSL/HTTPS on EC2 backend (nginx + certbot) | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 5 | Needed for Google OAuth + webhooks
REQ-INF-007 | api.sarveda-demo.xyz subdomain for backend | Technical | Must Have | Not Started | Not Started | Not Tested |  | Sprint 5
REQ-INF-008 | PM2 process manager for backend uptime | Technical | Must Have | Complete | Complete | Pass | sarveda-backend PM2 | Sprint 1
REQ-INF-009 | Razorpay webhook configured and verified | Technical | Must Have | Complete | Complete | Pass | Webhook set up | Sprint 2
REQ-INF-010 | Google OAuth credentials for sarveda-demo.xyz | Technical | Must Have | Complete | Complete | Pass | New Sarveda project in GCP | Sprint 2

## 🎓 Courses
🎓 Courses — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-CRS-001 | Course listing page | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-CRS-002 | Course purchase flow with Stripe/PayPal | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4 | International buyers primary
REQ-CRS-003 | Student portal — access purchased courses | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-CRS-004 | Live session Zoom link delivery after purchase | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-CRS-005 | Pre-recorded video course playback | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 4
REQ-CRS-006 | Course completion certificate | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 5
REQ-CRS-007 | Himalayan Retreat booking page with $900 pricing | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 4 | Highest ticket — priority

## 📣 Marketing
📣 Marketing — Requirements
REQ ID | Requirement | Source | Priority | Design | Dev | Test | Evidence | Sprint | Notes | Sign-off
REQ-MKT-001 | Google Analytics 4 integration | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Critical — start tracking from day 1
REQ-MKT-002 | Meta/Facebook Pixel integration | Arjun | Should Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-MKT-003 | Newsletter signup with email collection | Arjun | Must Have | Complete | Complete | Pass | NewsletterForm.tsx | Sprint 2
REQ-MKT-004 | Coupon code system — % and flat discount | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-MKT-005 | SEO — meta tags, OG tags, sitemap | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3
REQ-MKT-006 | Referral / affiliate program | Arjun | Nice to Have | Not Started | Not Started | Not Tested |  | Sprint 5
REQ-MKT-007 | WELCOME10 — 10% first order coupon | Arjun | Must Have | Not Started | Not Started | Not Tested |  | Sprint 3 | Already in announcement bar copy